## Sheet1
Req Id	Component	Description	Priority	DEV	STATUS
1	User Mgmt	User Login and Role Management	2
1.1	- GUI	User Login page / - User Name and password fields / - Show login errors on the same page / - On successful login, go to Main page	2	UJ, DK	DONE
1.2	- DB	User Table	2	UJ, DK	DONE
1.3	- Server	User Service, DAO, Controller	2	DK	DONE

2	Contact Mgnt	Contact and Group Management	1
2.1	- GUI	- Contact Edit Page (View, New, Edit, Delete) / - Contact Search Page / - Contact List Page / - Contact Priority DROP DOWN [NORMAL, MEDIUM, HIGH]	1	UJ, DK	DONE
2.2	- GUI	- Group Edit Page (View, New, Edit, Delete) / | - Group Name, Priority Only / - Group List Page / | - List group names, priority & No of members	1	UJ, DK	IN / PROGRESS
2.3	- GUI	- Contact Group Mapping Edit Page / | - Add Contact to Group / | - Remove Contact from Group / | - List of Contacts in the Group (EmpId, Name, Company, Number) / | - AJAX for Contact search by name	1	UJ, DK	IN / PROGRESS
	- DB	Contact, Group, ContactGroupMapping Tables	1	UJ, DK	DONE
	- Server	Contact Service, DAO, Controller	1	DK	DONE
	- Server	Group Service, DAO, Controller	1	DK	DONE
	- Server	ContactGroupMapping Service, DAO, Controller	1	DK	DONE

3	Template Mgmt	Message Template Management	2
3.1	- GUI	- Template Edit Page (View, New, Edit, Delete) / | - Template id and text only / - Template List Page	2	UJ, DK	DONE
3.2	- DB	Template Table	2	UJ, DK	DONE
3.3	- Server	Template Service, DAO, Controller	2	DK	DONE

4	Message Composer	Message Composer	1
4.1	- GUI	SMS Sending Page / - SMS Text Inbox (140 chars) / - SMS Template List Box / - Contact Groups List Box / - Contacts List Box / - Final List Box showing all selected Contacts / - Send SMS Button / - Retry count / >> On send button, assign the messages to Message Queue	1		IN / PROGRESS
4.2	- DB	NONE	1	UJ, DK	DONE
4.3	- Server	getAll() methods for – Message Template, Contact Groups, Contacts	1		DONE

5	Message Queue	Message Queue (Priority Queue)	1
5.1	- GUI	Status GUI / - Display the message list with status (counts of total | sent | pending | error) / - Display the message in a lable and show list of all the recipients (sent | pending | error) / - User needs to refresh for updating the status list (try AJAX)	2		NOT Started
5.2	- DB	Message Audit Table (individual message status logging)	2	UJ, DK	DONE
5.3	- Server	Distributed in-memory priority message queue structure	2
5.4	- Server	Message Audit Service, DAO, Controller	2		NOT Started

6	SMS Push	SMS Push API	1
6.1	- Server	- Multithreaded, Multi Modem API with 1 Modem per thread to send SMS / | - Use Java's Thread Pool Executor	1		NOT Started
6.2	- Server	- Manage pool of Push threads (worker) / - If times out, or connection breaks, / | - Remove the worker from the pool / | - Try disconnect / | - Try to re-connect for ever / | - On re-connect, re-assign to pool	1		NOT Started
6.3	- Server	- Wait on the Message Queue; / - As message arrives in the queue, start consuming and sending / - Log/ Update status in the Audit Table / - Retry on error for given number of times (re-queue messages) / - Pick messages by priority (1 = HIGH, 2 = NORMAL, 3 = LOW)	1		NOT Started

## Sheet2
Previous balance from Ganesh Ji's contribution	1270
Previous balance from Ruchi's farewell	700
Contribution for Deepti's farewell	2250
Gift for Deepti	-1960
Lunch	-2560
Balance	-300